## Meeting minutes
Team meeting minutes
ShadowVale
Location | Conference room |  |  | Facilitator | Nguyen Dinh Tai
Date | 2026-10-12 |  |  | Reporting period | 29 Sep - 12 Oct 2026
Time | 9:30 |  |  | Prepared | 2026-10-13
Agenda items
1. Review Unity environments, characters, cinematics and rescue gameplay.
2. Review web API integration, content workflow, accounts, analytics and solver features.
3. Review open version issues, hosting and automated deployment.
4. Include all experimental data and results in RBL Overleaf and confirm remaining actions.
Committed implementation remains In progress until acceptance is recorded. TBD means the owner or deadline is not agreed.
Action items
Action items | Owner(s) | Deadline | Status | Week 1 progress 29 Sep - 05 Oct 2026 | Week 2 progress 06 - 12 Oct 2026 | Notes
Implement Map 01 cinematics and rescue gameplay | Khoa | TBD | Completed | Added opening and extraction sequences, runtime systems and menu. | Added rescue, combat, stealth, crouch, stone throwing, save and audio. | Implemented. Acceptance pending.
Integrate Hung character assets and materials | T.Anh | TBD | In progress | Added character assets, mission setup and a separate skin material. | Integrated the character into the Map 01 rescue sequence. | Implemented. Acceptance pending.
Create Hung rescue animations | Thinh | TBD | Completed | Added tied, freed, limping and hit animations. | No further update recorded. | Implemented. Acceptance pending.
Develop Nam model and animations | Thinh | TBD | In progress | Imported Blender clips and added finger bones, gear and camouflage. | No further update recorded. | Implemented. Acceptance pending.
Develop Map 02 environment and arrival sequence | Tai, Khoa | TBD | Completed | Improved the village, models, sky, water and boundaries. | Added arrival cutscenes, animations, Vietnamese dialogue and scene updates. | Implemented. Acceptance pending.
Integrate web workspaces with backend APIs | Khoa | TBD | Completed | No web update recorded. | Connected content, review, publishing, analytics and solver APIs. Added account UI and language/theme controls. | End-to-end verification pending.
Build core APIs, analytics and data services | T.Anh | TBD | Completed | No web update recorded. | Added API layers, database migrations, telemetry, solver management, analytics, CSV export and tests. | Integrated verification pending.
Implement content authoring and version workflow | Thinh | TBD | Completed | No web update recorded. | Added Designer CRUD, version workflow, rollback, bundle download, detailed history and local configuration. | Workflow acceptance pending.
Implement authentication and user administration | Tai | TBD | Completed | No web update recorded. | Added Admin/user APIs and corrected token revocation, endpoint messages and JSON errors. | Role and session checks pending.
Deploy the frontend and backend to hosting | Khoa | TBD | Completed | No hosting update recorded. | Added Render/Docker configuration, production API documentation and frontend CORS settings. | Lecturer requirement. Verify both hosted services.
Automate frontend and backend deployment after CI | Khoa,Thịnh | TBD | Completed | No pipeline update recorded. | Added Render CD workflows after successful CI checks. | Lecturer requirement. Confirm successful hosted deployment.
Protect saved record keys in the content editor | Khoa,Thịnh | TBD | Completed | No web update recorded. | Locked saved primary/foreign keys and item type, including Weapon item. | Hosted verification pending.
Hide archived versions from Designer authoring | Khoa | TBD | Completed | No web update recorded. | Hidden archived versions and redirected old authoring links. | Hosted verification pending.
Correct content version soft deletion | Tai | TBD | Completed | No web update recorded. | Added a ContentVersion soft-delete fix. | Acceptance pending.
Restore access to older content versions | Khoa | TBD | Completed | No web update recorded. | Tracked the older-version listing issue. | Fix remains open in the minutes.
Fix page reload routing | Khoa | TBD | Completed | No web update recorded. | The minutes record the reload/Not Found fix as completed. | Retest hosted routes during release checks.
Revise solver logging | T,Anh | TBD | Completed | No progress recorded. | The minutes record solver logging as done. | Completion recorded in the source.
Run experiments and collect data | T,Anh | TBD | Completed | No experimental update recorded. | Collected data from four runs: one large and three small. | Data available. RBL publication tracked below.
Include all experimental data and results in RBL Overleaf | T,Anh | TBD | Completed | No RBL update recorded. | Experimental data available. Overleaf update remains pending. | Lecturer requirement. Include all data, setup and results.
Add hosting and CI/CD verification to the RBL report | T,Anh | TBD | In progress | No report update recorded. | No completed evidence section recorded in the minutes. | Include service URLs and successful pipeline/deployment evidence.
Sources: Google Docs meeting minutes, local Git history of both projects, and lecturer notes provided on 13 Oct 2026.
https://docs.google.com/document/d/1bZgsOxpzJap4Ygz-MR9M3vRuKzo1gYI8U6hbtVFI57k/edit
Repositories: github.com/dangkhoa31204/ShadowVale_web and github.com/anhttse184743/ShadowVale. Merge and stash entries excluded from work attribution.